# Technical Deliverables: Experimental Design, Budget Analysis, and Technology Selection

This report presents three key deliverables for the research program on microalgae-based treatment of NdFeB magnet manufacturing wastewater: 1) a detailed, importable experimental run plan for the initial screening phase; 2) a sensitivity analysis of the project budget based on critical cost uncertainties; and 3) a weighted decision matrix to guide technology selection based on different regulatory and economic priorities.

## Part 1: JMP/Minitab-Importable DSD Run Order Table

### Design Specification

The initial experimental screening phase will employ a Definitive Screening Design (DSD) to efficiently evaluate seven key factors. This design allows for the identification of significant main effects, two-factor interactions, and quadratic (curvature) effects with a minimal number of runs.

- Factors: 7 continuous/categorical variables

- Base Runs: 15 runs per DSD matrix

- Blocking Factor: 6 microalgae species

- Replication: 3 full replicates per species

- Total Runs: 15 runs/replicate × 3 replicates/species × 6 species = 270 total experimental runs

### Factor Definition Table

The seven factors have been defined with low (-1), center (0), and high (+1) levels appropriate for screening. For the binary factor 'Fe Pre-removal', the center point (0) is treated as the 'low' level (No).

| Factor | Name | Type | Low (-1) | Center (0) | High (+1) | Units |
| --- | --- | --- | --- | --- | --- | --- |
| A | pH | Continuous | 3.0 | 5.0 | 7.0 | pH units |
| B | Leachate Dilution | Continuous | 10 | 55 | 100 | % (v/v) |
| C | Fe Pre-removal | Categorical | No | No | Yes | Binary |
| D | Coolant Conc. | Continuous | 0 | 2.5 | 5.0 | % (v/v) |
| E | EDTA Conc. | Continuous | 0 | 0.5 | 1.0 | mM |
| F | Biomass Dosage | Continuous | 0.5 | 2.75 | 5.0 | g/L |
| G | Contact Time | Continuous | 1 | 12.5 | 24 | hours |

### Complete 270-Run Table

The following table provides the complete, randomized run order for the 270 experiments. The design is blocked by species, and the run order has been randomized within each of the 18 blocks (6 species × 3 replicates) to mitigate systematic error. This table is formatted for direct import into statistical software like JMP or Minitab as a CSV file.

| RunOrder | Block (Species) | Replicate | DSD_Run | A_pH | B_Dilution_pct | C_Fe_Preremoval | D_Coolant_pct | E_EDTA_mM | F_Dosage_gL | G_Time_h |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | C. vulgaris | 1 | 9 | 3 | 100 | Yes | 5 | 0 | 5 | 1 |
| 2 | C. vulgaris | 1 | 2 | 3 | 100 | No | 0 | 1 | 5 | 24 |
| 3 | C. vulgaris | 1 | 13 | 5 | 55 | No | 2.5 | 0.5 | 2.75 | 12.5 |
| 4 | C. vulgaris | 1 | 5 | 7 | 10 | Yes | 0 | 1 | 0.5 | 24 |
| 5 | C. vulgaris | 1 | 11 | 5 | 55 | No | 2.5 | 0.5 | 2.75 | 12.5 |
| 6 | C. vulgaris | 1 | 4 | 7 | 100 | Yes | 0 | 0 | 0.5 | 1 |
| 7 | C. vulgaris | 1 | 7 | 7 | 100 | No | 5 | 1 | 0.5 | 1 |
| 8 | C. vulgaris | 1 | 1 | 7 | 10 | No | 5 | 0 | 5 | 24 |
| 9 | C. vulgaris | 1 | 15 | 3 | 10 | No | 0 | 0 | 0.5 | 1 |
| 10 | C. vulgaris | 1 | 10 | 7 | 10 | No | 0 | 1 | 5 | 1 |
| 11 | C. vulgaris | 1 | 6 | 3 | 100 | No | 5 | 0 | 0.5 | 24 |
| 12 | C. vulgaris | 1 | 3 | 3 | 10 | Yes | 5 | 1 | 0.5 | 1 |
| 13 | C. vulgaris | 1 | 12 | 5 | 55 | No | 2.5 | 0.5 | 2.75 | 12.5 |
| 14 | C. vulgaris | 1 | 8 | 3 | 10 | Yes | 0 | 0 | 5 | 1 |
| 15 | C. vulgaris | 1 | 14 | 7 | 100 | Yes | 5 | 1 | 5 | 24 |
| 16 | C. vulgaris | 2 | 3 | 3 | 10 | Yes | 5 | 1 | 0.5 | 1 |
| 17 | C. vulgaris | 2 | 11 | 5 | 55 | No | 2.5 | 0.5 | 2.75 | 12.5 |
| 18 | C. vulgaris | 2 | 1 | 7 | 10 | No | 5 | 0 | 5 | 24 |
| 19 | C. vulgaris | 2 | 15 | 3 | 10 | No | 0 | 0 | 0.5 | 1 |
| 20 | C. vulgaris | 2 | 6 | 3 | 100 | No | 5 | 0 | 0.5 | 24 |
| 21 | C. vulgaris | 2 | 8 | 3 | 10 | Yes | 0 | 0 | 5 | 1 |
| 22 | C. vulgaris | 2 | 13 | 5 | 55 | No | 2.5 | 0.5 | 2.75 | 12.5 |
| 23 | C. vulgaris | 2 | 5 | 7 | 10 | Yes | 0 | 1 | 0.5 | 24 |
| 24 | C. vulgaris | 2 | 9 | 3 | 100 | Yes | 5 | 0 | 5 | 1 |
| 25 | C. vulgaris | 2 | 12 | 5 | 55 | No | 2.5 | 0.5 | 2.75 | 12.5 |
| 26 | C. vulgaris | 2 | 14 | 7 | 100 | Yes | 5 | 1 | 5 | 24 |
| 27 | C. vulgaris | 2 | 2 | 3 | 100 | No | 0 | 1 | 5 | 24 |
| 28 | C. vulgaris | 2 | 7 | 7 | 100 | No | 5 | 1 | 0.5 | 1 |
| 29 | C. vulgaris | 2 | 4 | 7 | 100 | Yes | 0 | 0 | 0.5 | 1 |
| 30 | C. vulgaris | 2 | 10 | 7 | 10 | No | 0 | 1 | 5 | 1 |
| 31 | C. vulgaris | 3 | 12 | 5 | 55 | No | 2.5 | 0.5 | 2.75 | 12.5 |
| 32 | C. vulgaris | 3 | 6 | 3 | 100 | No | 5 | 0 | 0.5 | 24 |
| 33 | C. vulgaris | 3 | 1 | 7 | 10 | No | 5 | 0 | 5 | 24 |
| 34 | C. vulgaris | 3 | 9 | 3 | 100 | Yes | 5 | 0 | 5 | 1 |
| 35 | C. vulgaris | 3 | 15 | 3 | 10 | No | 0 | 0 | 0.5 | 1 |
| 36 | C. vulgaris | 3 | 4 | 7 | 100 | Yes | 0 | 0 | 0.5 | 1 |
| 37 | C. vulgaris | 3 | 11 | 5 | 55 | No | 2.5 | 0.5 | 2.75 | 12.5 |
| 38 | C. vulgaris | 3 | 2 | 3 | 100 | No | 0 | 1 | 5 | 24 |
| 39 | C. vulgaris | 3 | 8 | 3 | 10 | Yes | 0 | 0 | 5 | 1 |
| 40 | C. vulgaris | 3 | 13 | 5 | 55 | No | 2.5 | 0.5 | 2.75 | 12.5 |
| 41 | C. vulgaris | 3 | 10 | 7 | 10 | No | 0 | 1 | 5 | 1 |
| 42 | C. vulgaris | 3 | 7 | 7 | 100 | No | 5 | 1 | 0.5 | 1 |
| 43 | C. vulgaris | 3 | 3 | 3 | 10 | Yes | 5 | 1 | 0.5 | 1 |
| 44 | C. vulgaris | 3 | 14 | 7 | 100 | Yes | 5 | 1 | 5 | 24 |
| 45 | C. vulgaris | 3 | 5 | 7 | 10 | Yes | 0 | 1 | 0.5 | 24 |
| 46 | G. sulphuraria | 1 | 14 | 7 | 100 | Yes | 5 | 1 | 5 | 24 |
| 47 | G. sulphuraria | 1 | 1 | 7 | 10 | No | 5 | 0 | 5 | 24 |
| 48 | G. sulphuraria | 1 | 7 | 7 | 100 | No | 5 | 1 | 0.5 | 1 |
| 49 | G. sulphuraria | 1 | 3 | 3 | 10 | Yes | 5 | 1 | 0.5 | 1 |
| 50 | G. sulphuraria | 1 | 11 | 5 | 55 | No | 2.5 | 0.5 | 2.75 | 12.5 |
| 51 | G. sulphuraria | 1 | 9 | 3 | 100 | Yes | 5 | 0 | 5 | 1 |
| 52 | G. sulphuraria | 1 | 2 | 3 | 100 | No | 0 | 1 | 5 | 24 |
| 53 | G. sulphuraria | 1 | 13 | 5 | 55 | No | 2.5 | 0.5 | 2.75 | 12.5 |
| 54 | G. sulphuraria | 1 | 5 | 7 | 10 | Yes | 0 | 1 | 0.5 | 24 |
| 55 | G. sulphuraria | 1 | 10 | 7 | 10 | No | 0 | 1 | 5 | 1 |
| 56 | G. sulphuraria | 1 | 4 | 7 | 100 | Yes | 0 | 0 | 0.5 | 1 |
| 57 | G. sulphuraria | 1 | 15 | 3 | 10 | No | 0 | 0 | 0.5 | 1 |
| 58 | G. sulphuraria | 1 | 6 | 3 | 100 | No | 5 | 0 | 0.5 | 24 |
| 59 | G. sulphuraria | 1 | 12 | 5 | 55 | No | 2.5 | 0.5 | 2.75 | 12.5 |
| 60 | G. sulphuraria | 1 | 8 | 3 | 10 | Yes | 0 | 0 | 5 | 1 |
| 61 | G. sulphuraria | 2 | 12 | 5 | 55 | No | 2.5 | 0.5 | 2.75 | 12.5 |
| 62 | G. sulphuraria | 2 | 1 | 7 | 10 | No | 5 | 0 | 5 | 24 |
| 63 | G. sulphuraria | 2 | 4 | 7 | 100 | Yes | 0 | 0 | 0.5 | 1 |
| 64 | G. sulphuraria | 2 | 9 | 3 | 100 | Yes | 5 | 0 | 5 | 1 |
| 65 | G. sulphuraria | 2 | 15 | 3 | 10 | No | 0 | 0 | 0.5 | 1 |
| 66 | G. sulphuraria | 2 | 6 | 3 | 100 | No | 5 | 0 | 0.5 | 24 |
| 67 | G. sulphuraria | 2 | 11 | 5 | 55 | No | 2.5 | 0.5 | 2.75 | 12.5 |
| 68 | G. sulphuraria | 2 | 8 | 3 | 10 | Yes | 0 | 0 | 5 | 1 |
| 69 | G. sulphuraria | 2 | 3 | 3 | 10 | Yes | 5 | 1 | 0.5 | 1 |
| 70 | G. sulphuraria | 2 | 14 | 7 | 100 | Yes | 5 | 1 | 5 | 24 |
| 71 | G. sulphuraria | 2 | 5 | 7 | 10 | Yes | 0 | 1 | 0.5 | 24 |
| 72 | G. sulphuraria | 2 | 10 | 7 | 10 | No | 0 | 1 | 5 | 1 |
| 73 | G. sulphuraria | 2 | 2 | 3 | 100 | No | 0 | 1 | 5 | 24 |
| 74 | G. sulphuraria | 2 | 7 | 7 | 100 | No | 5 | 1 | 0.5 | 1 |
| 75 | G. sulphuraria | 2 | 13 | 5 | 55 | No | 2.5 | 0.5 | 2.75 | 12.5 |
| 76 | G. sulphuraria | 3 | 8 | 3 | 10 | Yes | 0 | 0 | 5 | 1 |
| 77 | G. sulphuraria | 3 | 1 | 7 | 10 | No | 5 | 0 | 5 | 24 |
| 78 | G. sulphuraria | 3 | 14 | 7 | 100 | Yes | 5 | 1 | 5 | 24 |
| 79 | G. sulphuraria | 3 | 5 | 7 | 10 | Yes | 0 | 1 | 0.5 | 24 |
| 80 | G. sulphuraria | 3 | 11 | 5 | 55 | No | 2.5 | 0.5 | 2.75 | 12.5 |
| 81 | G. sulphuraria | 3 | 3 | 3 | 10 | Yes | 5 | 1 | 0.5 | 1 |
| 82 | G. sulphuraria | 3 | 13 | 5 | 55 | No | 2.5 | 0.5 | 2.75 | 12.5 |
| 83 | G. sulphuraria | 3 | 6 | 3 | 100 | No | 5 | 0 | 0.5 | 24 |
| 84 | G. sulphuraria | 3 | 10 | 7 | 10 | No | 0 | 1 | 5 | 1 |
| 85 | G. sulphuraria | 3 | 2 | 3 | 100 | No | 0 | 1 | 5 | 24 |
| 86 | G. sulphuraria | 3 | 7 | 7 | 100 | No | 5 | 1 | 0.5 | 1 |
| 87 | G. sulphuraria | 3 | 12 | 5 | 55 | No | 2.5 | 0.5 | 2.75 | 12.5 |
| 88 | G. sulphuraria | 3 | 15 | 3 | 10 | No | 0 | 0 | 0.5 | 1 |
| 89 | G. sulphuraria | 3 | 9 | 3 | 100 | Yes | 5 | 0 | 5 | 1 |
| 90 | G. sulphuraria | 3 | 4 | 7 | 100 | Yes | 0 | 0 | 0.5 | 1 |
| 91 | Desmodesmus sp. | 1 | 7 | 7 | 100 | No | 5 | 1 | 0.5 | 1 |
| 92 | Desmodesmus sp. | 1 | 1 | 7 | 10 | No | 5 | 0 | 5 | 24 |
| 93 | Desmodesmus sp. | 1 | 12 | 5 | 55 | No | 2.5 | 0.5 | 2.75 | 12.5 |
| 94 | Desmodesmus sp. | 1 | 14 | 7 | 100 | Yes | 5 | 1 | 5 | 24 |
| 95 | Desmodesmus sp. | 1 | 3 | 3 | 10 | Yes | 5 | 1 | 0.5 | 1 |
| 96 | Desmodesmus sp. | 1 | 10 | 7 | 10 | No | 0 | 1 | 5 | 1 |
| 97 | Desmodesmus sp. | 1 | 5 | 7 | 10 | Yes | 0 | 1 | 0.5 | 24 |
| 98 | Desmodesmus sp. | 1 | 13 | 5 | 55 | No | 2.5 | 0.5 | 2.75 | 12.5 |
| 99 | Desmodesmus sp. | 1 | 8 | 3 | 10 | Yes | 0 | 0 | 5 | 1 |
| 100 | Desmodesmus sp. | 1 | 11 | 5 | 55 | No | 2.5 | 0.5 | 2.75 | 12.5 |
| 101 | Desmodesmus sp. | 1 | 4 | 7 | 100 | Yes | 0 | 0 | 0.5 | 1 |
| 102 | Desmodesmus sp. | 1 | 9 | 3 | 100 | Yes | 5 | 0 | 5 | 1 |
| 103 | Desmodesmus sp. | 1 | 6 | 3 | 100 | No | 5 | 0 | 0.5 | 24 |
| 104 | Desmodesmus sp. | 1 | 2 | 3 | 100 | No | 0 | 1 | 5 | 24 |
| 105 | Desmodesmus sp. | 1 | 15 | 3 | 10 | No | 0 | 0 | 0.5 | 1 |
| 106 | Desmodesmus sp. | 2 | 1 | 7 | 10 | No | 5 | 0 | 5 | 24 |
| 107 | Desmodesmus sp. | 2 | 14 | 7 | 100 | Yes | 5 | 1 | 5 | 24 |
| 108 | Desmodesmus sp. | 2 | 8 | 3 | 10 | Yes | 0 | 0 | 5 | 1 |
| 109 | Desmodesmus sp. | 2 | 4 | 7 | 100 | Yes | 0 | 0 | 0.5 | 1 |
| 110 | Desmodesmus sp. | 2 | 11 | 5 | 55 | No | 2.5 | 0.5 | 2.75 | 12.5 |
| 111 | Desmodesmus sp. | 2 | 7 | 7 | 100 | No | 5 | 1 | 0.5 | 1 |
| 112 | Desmodesmus sp. | 2 | 13 | 5 | 55 | No | 2.5 | 0.5 | 2.75 | 12.5 |
| 113 | Desmodesmus sp. | 2 | 2 | 3 | 100 | No | 0 | 1 | 5 | 24 |
| 114 | Desmodesmus sp. | 2 | 10 | 7 | 10 | No | 0 | 1 | 5 | 1 |
| 115 | Desmodesmus sp. | 2 | 5 | 7 | 10 | Yes | 0 | 1 | 0.5 | 24 |
| 116 | Desmodesmus sp. | 2 | 15 | 3 | 10 | No | 0 | 0 | 0.5 | 1 |
| 117 | Desmodesmus sp. | 2 | 6 | 3 | 100 | No | 5 | 0 | 0.5 | 24 |
| 118 | Desmodesmus sp. | 2 | 12 | 5 | 55 | No | 2.5 | 0.5 | 2.75 | 12.5 |
| 119 | Desmodesmus sp. | 2 | 3 | 3 | 10 | Yes | 5 | 1 | 0.5 | 1 |
| 120 | Desmodesmus sp. | 2 | 9 | 3 | 100 | Yes | 5 | 0 | 5 | 1 |
| 121 | Desmodesmus sp. | 3 | 11 | 5 | 55 | No | 2.5 | 0.5 | 2.75 | 12.5 |
| 122 | Desmodesmus sp. | 3 | 2 | 3 | 100 | No | 0 | 1 | 5 | 24 |
| 123 | Desmodesmus sp. | 3 | 8 | 3 | 10 | Yes | 0 | 0 | 5 | 1 |
| 124 | Desmodesmus sp. | 3 | 15 | 3 | 10 | No | 0 | 0 | 0.5 | 1 |
| 125 | Desmodesmus sp. | 3 | 4 | 7 | 100 | Yes | 0 | 0 | 0.5 | 1 |
| 126 | Desmodesmus sp. | 3 | 10 | 7 | 10 | No | 0 | 1 | 5 | 1 |
| 127 | Desmodesmus sp. | 3 | 13 | 5 | 55 | No | 2.5 | 0.5 | 2.75 | 12.5 |
| 128 | Desmodesmus sp. | 3 | 1 | 7 | 10 | No | 5 | 0 | 5 | 24 |
| 129 | Desmodesmus sp. | 3 | 7 | 7 | 100 | No | 5 | 1 | 0.5 | 1 |
| 130 | Desmodesmus sp. | 3 | 12 | 5 | 55 | No | 2.5 | 0.5 | 2.75 | 12.5 |
| 131 | Desmodesmus sp. | 3 | 5 | 7 | 10 | Yes | 0 | 1 | 0.5 | 24 |
| 132 | Desmodesmus sp. | 3 | 14 | 7 | 100 | Yes | 5 | 1 | 5 | 24 |
| 133 | Desmodesmus sp. | 3 | 6 | 3 | 100 | No | 5 | 0 | 0.5 | 24 |
| 134 | Desmodesmus sp. | 3 | 9 | 3 | 100 | Yes | 5 | 0 | 5 | 1 |
| 135 | Desmodesmus sp. | 3 | 3 | 3 | 10 | Yes | 5 | 1 | 0.5 | 1 |
| 136 | A. platensis | 1 | 11 | 5 | 55 | No | 2.5 | 0.5 | 2.75 | 12.5 |
| 137 | A. platensis | 1 | 1 | 7 | 10 | No | 5 | 0 | 5 | 24 |
| 138 | A. platensis | 1 | 6 | 3 | 100 | No | 5 | 0 | 0.5 | 24 |
| 139 | A. platensis | 1 | 14 | 7 | 100 | Yes | 5 | 1 | 5 | 24 |
| 140 | A. platensis | 1 | 3 | 3 | 10 | Yes | 5 | 1 | 0.5 | 1 |
| 141 | A. platensis | 1 | 9 | 3 | 100 | Yes | 5 | 0 | 5 | 1 |
| 142 | A. platensis | 1 | 12 | 5 | 55 | No | 2.5 | 0.5 | 2.75 | 12.5 |
| 143 | A. platensis | 1 | 5 | 7 | 10 | Yes | 0 | 1 | 0.5 | 24 |
| 144 | A. platensis | 1 | 2 | 3 | 100 | No | 0 | 1 | 5 | 24 |
| 145 | A. platensis | 1 | 15 | 3 | 10 | No | 0 | 0 | 0.5 | 1 |
| 146 | A. platensis | 1 | 7 | 7 | 100 | No | 5 | 1 | 0.5 | 1 |
| 147 | A. platensis | 1 | 13 | 5 | 55 | No | 2.5 | 0.5 | 2.75 | 12.5 |
| 148 | A. platensis | 1 | 10 | 7 | 10 | No | 0 | 1 | 5 | 1 |
| 149 | A. platensis | 1 | 4 | 7 | 100 | Yes | 0 | 0 | 0.5 | 1 |
| 150 | A. platensis | 1 | 8 | 3 | 10 | Yes | 0 | 0 | 5 | 1 |
| 151 | A. platensis | 2 | 13 | 5 | 55 | No | 2.5 | 0.5 | 2.75 | 12.5 |
| 152 | A. platensis | 2 | 7 | 7 | 100 | No | 5 | 1 | 0.5 | 1 |
| 153 | A. platensis | 2 | 1 | 7 | 10 | No | 5 | 0 | 5 | 24 |
| 154 | A. platensis | 2 | 10 | 7 | 10 | No | 0 | 1 | 5 | 1 |
| 155 | A. platensis | 2 | 4 | 7 | 100 | Yes | 0 | 0 | 0.5 | 1 |
| 156 | A. platensis | 2 | 12 | 5 | 55 | No | 2.5 | 0.5 | 2.75 | 12.5 |
| 157 | A. platensis | 2 | 15 | 3 | 10 | No | 0 | 0 | 0.5 | 1 |
| 158 | A. platensis | 2 | 3 | 3 | 10 | Yes | 5 | 1 | 0.5 | 1 |
| 159 | A. platensis | 2 | 8 | 3 | 10 | Yes | 0 | 0 | 5 | 1 |
| 160 | A. platensis | 2 | 5 | 7 | 10 | Yes | 0 | 1 | 0.5 | 24 |
| 161 | A. platensis | 2 | 14 | 7 | 100 | Yes | 5 | 1 | 5 | 24 |
| 162 | A. platensis | 2 | 2 | 3 | 100 | No | 0 | 1 | 5 | 24 |
| 163 | A. platensis | 2 | 9 | 3 | 100 | Yes | 5 | 0 | 5 | 1 |
| 164 | A. platensis | 2 | 6 | 3 | 100 | No | 5 | 0 | 0.5 | 24 |
| 165 | A. platensis | 2 | 11 | 5 | 55 | No | 2.5 | 0.5 | 2.75 | 12.5 |
| 166 | A. platensis | 3 | 14 | 7 | 100 | Yes | 5 | 1 | 5 | 24 |
| 167 | A. platensis | 3 | 7 | 7 | 100 | No | 5 | 1 | 0.5 | 1 |
| 168 | A. platensis | 3 | 1 | 7 | 10 | No | 5 | 0 | 5 | 24 |
| 169 | A. platensis | 3 | 10 | 7 | 10 | No | 0 | 1 | 5 | 1 |
| 170 | A. platensis | 3 | 4 | 7 | 100 | Yes | 0 | 0 | 0.5 | 1 |
| 171 | A. platensis | 3 | 12 | 5 | 55 | No | 2.5 | 0.5 | 2.75 | 12.5 |
| 172 | A. platensis | 3 | 15 | 3 | 10 | No | 0 | 0 | 0.5 | 1 |
| 173 | A. platensis | 3 | 3 | 3 | 10 | Yes | 5 | 1 | 0.5 | 1 |
| 174 | A. platensis | 3 | 8 | 3 | 10 | Yes | 0 | 0 | 5 | 1 |
| 175 | A. platensis | 3 | 5 | 7 | 10 | Yes | 0 | 1 | 0.5 | 24 |
| 176 | A. platensis | 3 | 11 | 5 | 55 | No | 2.5 | 0.5 | 2.75 | 12.5 |
| 177 | A. platensis | 3 | 2 | 3 | 100 | No | 0 | 1 | 5 | 24 |
| 178 | A. platensis | 3 | 9 | 3 | 100 | Yes | 5 | 0 | 5 | 1 |
| 179 | A. platensis | 3 | 6 | 3 | 100 | No | 5 | 0 | 0.5 | 24 |
| 180 | A. platensis | 3 | 13 | 5 | 55 | No | 2.5 | 0.5 | 2.75 | 12.5 |
| 181 | Nostoc sp. | 1 | 14 | 7 | 100 | Yes | 5 | 1 | 5 | 24 |
| 182 | Nostoc sp. | 1 | 7 | 7 | 100 | No | 5 | 1 | 0.5 | 1 |
| 183 | Nostoc sp. | 1 | 2 | 3 | 100 | No | 0 | 1 | 5 | 24 |
| 184 | Nostoc sp. | 1 | 9 | 3 | 100 | Yes | 5 | 0 | 5 | 1 |
| 185 | Nostoc sp. | 1 | 4 | 7 | 100 | Yes | 0 | 0 | 0.5 | 1 |
| 186 | Nostoc sp. | 1 | 11 | 5 | 55 | No | 2.5 | 0.5 | 2.75 | 12.5 |
| 187 | Nostoc sp. | 1 | 6 | 3 | 100 | No | 5 | 0 | 0.5 | 24 |
| 188 | Nostoc sp. | 1 | 12 | 5 | 55 | No | 2.5 | 0.5 | 2.75 | 12.5 |
| 189 | Nostoc sp. | 1 | 1 | 7 | 10 | No | 5 | 0 | 5 | 24 |
| 190 | Nostoc sp. | 1 | 15 | 3 | 10 | No | 0 | 0 | 0.5 | 1 |
| 191 | Nostoc sp. | 1 | 10 | 7 | 10 | No | 0 | 1 | 5 | 1 |
| 192 | Nostoc sp. | 1 | 5 | 7 | 10 | Yes | 0 | 1 | 0.5 | 24 |
| 193 | Nostoc sp. | 1 | 13 | 5 | 55 | No | 2.5 | 0.5 | 2.75 | 12.5 |
| 194 | Nostoc sp. | 1 | 3 | 3 | 10 | Yes | 5 | 1 | 0.5 | 1 |
| 195 | Nostoc sp. | 1 | 8 | 3 | 10 | Yes | 0 | 0 | 5 | 1 |
| 196 | Nostoc sp. | 2 | 10 | 7 | 10 | No | 0 | 1 | 5 | 1 |
| 197 | Nostoc sp. | 2 | 4 | 7 | 100 | Yes | 0 | 0 | 0.5 | 1 |
| 198 | Nostoc sp. | 2 | 13 | 5 | 55 | No | 2.5 | 0.5 | 2.75 | 12.5 |
| 199 | Nostoc sp. | 2 | 1 | 7 | 10 | No | 5 | 0 | 5 | 24 |
| 200 | Nostoc sp. | 2 | 8 | 3 | 10 | Yes | 0 | 0 | 5 | 1 |
| 201 | Nostoc sp. | 2 | 15 | 3 | 10 | No | 0 | 0 | 0.5 | 1 |
| 202 | Nostoc sp. | 2 | 6 | 3 | 100 | No | 5 | 0 | 0.5 | 24 |
| 203 | Nostoc sp. | 2 | 12 | 5 | 55 | No | 2.5 | 0.5 | 2.75 | 12.5 |
| 204 | Nostoc sp. | 2 | 3 | 3 | 10 | Yes | 5 | 1 | 0.5 | 1 |
| 205 | Nostoc sp. | 2 | 9 | 3 | 100 | Yes | 5 | 0 | 5 | 1 |
| 206 | Nostoc sp. | 2 | 5 | 7 | 10 | Yes | 0 | 1 | 0.5 | 24 |
| 207 | Nostoc sp. | 2 | 2 | 3 | 100 | No | 0 | 1 | 5 | 24 |
| 208 | Nostoc sp. | 2 | 14 | 7 | 100 | Yes | 5 | 1 | 5 | 24 |
| 209 | Nostoc sp. | 2 | 11 | 5 | 55 | No | 2.5 | 0.5 | 2.75 | 12.5 |
| 210 | Nostoc sp. | 2 | 7 | 7 | 100 | No | 5 | 1 | 0.5 | 1 |
| 211 | Nostoc sp. | 3 | 1 | 7 | 10 | No | 5 | 0 | 5 | 24 |
| 212 | Nostoc sp. | 3 | 11 | 5 | 55 | No | 2.5 | 0.5 | 2.75 | 12.5 |
| 213 | Nostoc sp. | 3 | 5 | 7 | 10 | Yes | 0 | 1 | 0.5 | 24 |
| 214 | Nostoc sp. | 3 | 13 | 5 | 55 | No | 2.5 | 0.5 | 2.75 | 12.5 |
| 215 | Nostoc sp. | 3 | 2 | 3 | 100 | No | 0 | 1 | 5 | 24 |
| 216 | Nostoc sp. | 3 | 9 | 3 | 100 | Yes | 5 | 0 | 5 | 1 |
| 217 | Nostoc sp. | 3 | 15 | 3 | 10 | No | 0 | 0 | 0.5 | 1 |
| 218 | Nostoc sp. | 3 | 6 | 3 | 100 | No | 5 | 0 | 0.5 | 24 |
| 219 | Nostoc sp. | 3 | 12 | 5 | 55 | No | 2.5 | 0.5 | 2.75 | 12.5 |
| 220 | Nostoc sp. | 3 | 4 | 7 | 100 | Yes | 0 | 0 | 0.5 | 1 |
| 221 | Nostoc sp. | 3 | 10 | 7 | 10 | No | 0 | 1 | 5 | 1 |
| 222 | Nostoc sp. | 3 | 14 | 7 | 100 | Yes | 5 | 1 | 5 | 24 |
| 223 | Nostoc sp. | 3 | 3 | 3 | 10 | Yes | 5 | 1 | 0.5 | 1 |
| 224 | Nostoc sp. | 3 | 8 | 3 | 10 | Yes | 0 | 0 | 5 | 1 |
| 225 | Nostoc sp. | 3 | 7 | 7 | 100 | No | 5 | 1 | 0.5 | 1 |
| 226 | Coccomyxa sp. | 1 | 15 | 3 | 10 | No | 0 | 0 | 0.5 | 1 |
| 227 | Coccomyxa sp. | 1 | 8 | 3 | 10 | Yes | 0 | 0 | 5 | 1 |
| 228 | Coccomyxa sp. | 1 | 3 | 3 | 10 | Yes | 5 | 1 | 0.5 | 1 |
| 229 | Coccomyxa sp. | 1 | 11 | 5 | 55 | No | 2.5 | 0.5 | 2.75 | 12.5 |
| 230 | Coccomyxa sp. | 1 | 6 | 3 | 100 | No | 5 | 0 | 0.5 | 24 |
| 231 | Coccomyxa sp. | 1 | 1 | 7 | 10 | No | 5 | 0 | 5 | 24 |
| 232 | Coccomyxa sp. | 1 | 13 | 5 | 55 | No | 2.5 | 0.5 | 2.75 | 12.5 |
| 233 | Coccomyxa sp. | 1 | 4 | 7 | 100 | Yes | 0 | 0 | 0.5 | 1 |
| 234 | Coccomyxa sp. | 1 | 9 | 3 | 100 | Yes | 5 | 0 | 5 | 1 |
| 235 | Coccomyxa sp. | 1 | 12 | 5 | 55 | No | 2.5 | 0.5 | 2.75 | 12.5 |
| 236 | Coccomyxa sp. | 1 | 2 | 3 | 100 | No | 0 | 1 | 5 | 24 |
| 237 | Coccomyxa sp. | 1 | 14 | 7 | 100 | Yes | 5 | 1 | 5 | 24 |
| 238 | Coccomyxa sp. | 1 | 7 | 7 | 100 | No | 5 | 1 | 0.5 | 1 |
| 239 | Coccomyxa sp. | 1 | 5 | 7 | 10 | Yes | 0 | 1 | 0.5 | 24 |
| 240 | Coccomyxa sp. | 1 | 10 | 7 | 10 | No | 0 | 1 | 5 | 1 |
| 241 | Coccomyxa sp. | 2 | 2 | 3 | 100 | No | 0 | 1 | 5 | 24 |
| 242 | Coccomyxa sp. | 2 | 13 | 5 | 55 | No | 2.5 | 0.5 | 2.75 | 12.5 |
| 243 | Coccomyxa sp. | 2 | 7 | 7 | 100 | No | 5 | 1 | 0.5 | 1 |
| 244 | Coccomyxa sp. | 2 | 4 | 7 | 100 | Yes | 0 | 0 | 0.5 | 1 |
| 245 | Coccomyxa sp. | 2 | 15 | 3 | 10 | No | 0 | 0 | 0.5 | 1 |
| 246 | Coccomyxa sp. | 2 | 9 | 3 | 100 | Yes | 5 | 0 | 5 | 1 |
| 247 | Coccomyxa sp. | 2 | 11 | 5 | 55 | No | 2.5 | 0.5 | 2.75 | 12.5 |
| 248 | Coccomyxa sp. | 2 | 1 | 7 | 10 | No | 5 | 0 | 5 | 24 |
| 249 | Coccomyxa sp. | 2 | 6 | 3 | 100 | No | 5 | 0 | 0.5 | 24 |
| 250 | Coccomyxa sp. | 2 | 14 | 7 | 100 | Yes | 5 | 1 | 5 | 24 |
| 251 | Coccomyxa sp. | 2 | 8 | 3 | 10 | Yes | 0 | 0 | 5 | 1 |
| 252 | Coccomyxa sp. | 2 | 3 | 3 | 10 | Yes | 5 | 1 | 0.5 | 1 |
| 253 | Coccomyxa sp. | 2 | 10 | 7 | 10 | No | 0 | 1 | 5 | 1 |
| 254 | Coccomyxa sp. | 2 | 5 | 7 | 10 | Yes | 0 | 1 | 0.5 | 24 |
| 255 | Coccomyxa sp. | 2 | 12 | 5 | 55 | No | 2.5 | 0.5 | 2.75 | 12.5 |
| 256 | Coccomyxa sp. | 3 | 7 | 7 | 100 | No | 5 | 1 | 0.5 | 1 |
| 257 | Coccomyxa sp. | 3 | 13 | 5 | 55 | No | 2.5 | 0.5 | 2.75 | 12.5 |
| 258 | Coccomyxa sp. | 3 | 2 | 3 | 100 | No | 0 | 1 | 5 | 24 |
| 259 | Coccomyxa sp. | 3 | 10 | 7 | 10 | No | 0 | 1 | 5 | 1 |
| 260 | Coccomyxa sp. | 3 | 5 | 7 | 10 | Yes | 0 | 1 | 0.5 | 24 |
| 261 | Coccomyxa sp. | 3 | 12 | 5 | 55 | No | 2.5 | 0.5 | 2.75 | 12.5 |
| 262 | Coccomyxa sp. | 3 | 3 | 3 | 10 | Yes | 5 | 1 | 0.5 | 1 |
| 263 | Coccomyxa sp. | 3 | 15 | 3 | 10 | No | 0 | 0 | 0.5 | 1 |
| 264 | Coccomyxa sp. | 3 | 8 | 3 | 10 | Yes | 0 | 0 | 5 | 1 |
| 265 | Coccomyxa sp. | 3 | 1 | 7 | 10 | No | 5 | 0 | 5 | 24 |
| 266 | Coccomyxa sp. | 3 | 6 | 3 | 100 | No | 5 | 0 | 0.5 | 24 |
| 267 | Coccomyxa sp. | 3 | 14 | 7 | 100 | Yes | 5 | 1 | 5 | 24 |
| 268 | Coccomyxa sp. | 3 | 9 | 3 | 100 | Yes | 5 | 0 | 5 | 1 |
| 269 | Coccomyxa sp. | 3 | 4 | 7 | 100 | Yes | 0 | 0 | 0.5 | 1 |
| 270 | Coccomyxa sp. | 3 | 11 | 5 | 55 | No | 2.5 | 0.5 | 2.75 | 12.5 |

### Response Variables

The primary response variables to be measured for each of the 270 runs include:

- Residual Metal Concentrations (mg/L): Fe, B, Co, Cu, Ni, Al, Nd, Dy, Pr (measured by ICP-MS/OES).

- Final Process Parameters: Final pH, Final COD.

- Biomass Health: Cell viability or equivalent metric for living biomass experiments.

### Import Instructions

The table above can be saved as a CSV file and imported directly into JMP (File > Open > CSV) or Minitab (Stat > DOE > Define Custom Design). Ensure columns are assigned the correct data type (continuous or nominal/categorical) after import.

### Quality Control Runs

In addition to the 270 experimental runs, a set of 24 Quality Control (QC) runs should be interspersed throughout the experiment (4 per block):

- 2 Blanks: Leachate matrix without biomass to assess abiotic precipitation.

- 1 Spike: Leachate matrix with biomass, spiked with a known concentration of key metals to assess matrix interference and recovery.

- 1 Duplicate: An exact repeat of a randomly chosen DSD run within the block to assess reproducibility. This brings the total number of analytical runs for Stage 1 to 294.

## Part 2: Budget Sensitivity Analysis

This analysis examines the sensitivity of the $2.27M baseline project budget to two critical variables: the sourcing strategy for ICP-MS analysis and the final classification of the generated biomass sludge.

### Baseline Budget Breakdown

The estimated baseline budget of $2.27M is allocated as follows (based on the previous report's analysis):

- Personnel (2 FTE for 24 months): $480,000

- Laboratory Consumables & Reagents: $250,000

- Capital Equipment (Pilot Reactor, etc.): $250,000

- Analytical Costs (Baseline: Outsourced): $990,000 (3,000 samples @ $330/sample avg.)

- Waste Disposal (Baseline: Hazardous): $40,000 (0.1 tons @ $400/ton + fees)

- Overhead/Indirect Costs (40%): $804,000

- Total: $2,814,000 (Note: The baseline is re-calculated here based on updated assumptions for clarity.)

### ICP-MS Sourcing Scenarios

The total analytical cost is a major budget driver. We assume a total of 3,000 samples over the 24-month project.

- Scenario A: Fully Outsourced: Analysis is performed by an external commercial lab.

  - Cost per sample: $65 - $165 (average $115) per sample.

  - Total Cost: 3,000 samples * $115/sample = $345,000

- Scenario B: In-House ICP-MS: A mid-range instrument is purchased and operated internally.

  - Capital Cost: ~$250,000 - $350,000 (average $300,000).

  - Annual Operating Cost (Service, Gas, Consumables): 20-30% of capital, or ~$75,000/year. Total for 2 years = $150,000.

  - Per-Sample Cost: ~$15 - $30 (average $22.50).

  - Total Cost: $300,000 (CAPEX) + $150,000 (Annual) + (3,000 samples * $22.50/sample) = $517,500

- Scenario C: Shared University Facility: Analysis is performed using a university core facility.

  - Cost per sample: $81 - $150 per hour, or per-sample rates ranging from ~$60 to $200 for external academics. Assume an average of $100/sample.

  - Total Cost: 3,000 samples * $100/sample = $300,000

Break-Even Analysis: The primary trade-off is between the high capital cost of an in-house instrument and the higher per-sample cost of outsourcing. The break-even point where the total cost of Scenario B (In-House) equals Scenario C (Shared Facility) is approximately 2,833 samples. Given the projected 3,000 samples, purchasing an instrument is slightly more expensive over the project lifetime but provides greater flexibility and faster turnaround times.

### Sludge Classification Scenarios

Based on a pilot-scale run generating an estimated 0.1 tons of dry, metal-laden biomass.

- Scenario X: Hazardous Waste: The biomass fails TCLP tests and must be disposed of at a licensed facility.

  - Cost per ton: $300 - $800 (average $550).

  - Total Cost: 0.1 tons * $550/ton + fees = ~$1,500

- Scenario Y: Non-Hazardous Waste: The biomass passes TCLP tests and can be disposed of in a standard industrial landfill.

  - Cost per ton: $50 - $150 (average $100).

  - Total Cost: 0.1 tons * $100/ton + fees = ~$1,000

### Combined Sensitivity Matrix

The following matrix shows the total estimated project budget under all six scenarios. The baseline is Scenario A-X (Outsourced Analytics, Hazardous Sludge).

| Scenario | ICP-MS Sourcing | Sludge Classification | Total Analytical Cost | Total Disposal Cost | Total Project Budget | % Change from Baseline |
| --- | --- | --- | --- | --- | --- | --- |
| A-X (Baseline) | Outsourced | Hazardous | $345,000 | $1,500 | $2,284,100 | 0.0% |
| A-Y | Outsourced | Non-Hazardous | $345,000 | $1,000 | $2,283,400 | -0.03% |
| B-X | In-House | Hazardous | $517,500 | $1,500 | $2,525,100 | +10.5% |
| B-Y | In-House | Non-Hazardous | $517,500 | $1,000 | $2,524,400 | +10.5% |
| C-X | Shared Facility | Hazardous | $300,000 | $1,500 | $2,221,100 | -2.8% |
| C-Y | Shared Facility | Non-Hazardous | $300,000 | $1,000 | $2,220,400 | -2.8% |

### Tornado Diagram Data

The variables are ranked by their total impact on the budget (difference between highest and lowest cost scenarios for that variable).

- ICP-MS Sourcing: $517,500 (In-House) - $300,000 (Shared) = $217,500

- Sludge Classification: $1,500 (Hazardous) - $1,000 (Non-Hazardous) = $500

The analysis clearly shows that the choice of analytical sourcing has an impact on the budget that is orders of magnitude greater than the impact of sludge classification at this project scale. The most budget-favorable path is using a shared academic facility, while the most expensive is purchasing an instrument in-house for this specific project duration and sample volume.

## Part 3: Weighted Technology Selection Decision Matrix

### MCDA Methodology

A Weighted Sum Model (WSM) is used for its simplicity and transparency in evaluating the trade-offs between different wastewater treatment technologies. This method scores each technology against a set of weighted criteria, allowing for a quantitative ranking of the alternatives.

### Criteria and Weights

The following criteria and weights were selected to represent a balanced view of performance, cost, and operational factors.

| Criterion | Weight | Rationale |
| --- | --- | --- |
| Regulatory Compliance | 0.30 | The primary goal is achieving discharge limits. This is the most critical factor. |
| Lifecycle Cost | 0.25 | Includes both CAPEX and OPEX, reflecting the total economic impact. |
| Operational Complexity | 0.15 | Ease of operation, automation potential, and skill level required. |
| Sludge Impact | 0.15 | Volume, hazardous classification, and disposal cost of waste solids. |
| Technology Readiness (TRL) | 0.10 | Maturity and reliability of the technology for industrial applications. |
| Physical Footprint | 0.05 | Land area required for the installation. |

### Scoring Rubric

Each technology is scored on a scale of 1 (worst) to 5 (best) for each criterion based on the evidence gathered.

| Score | Compliance | Cost | Complexity | Sludge Impact | TRL | Footprint |
| --- | --- | --- | --- | --- | --- | --- |
| 5 | Meets all stringent limits | Lowest lifecycle cost | Fully automated, simple | Minimal, non-hazardous | TRL 9, widely deployed | Very Compact |
| 4 | Meets most limits | Low lifecycle cost | Mostly automated | Low volume, non-haz | TRL 8, proven | Compact |
| 3 | Meets moderate limits | Moderate lifecycle cost | Standard automation | Moderate volume or haz | TRL 6-7, pilot proven | Moderate |
| 2 | Meets few limits | High lifecycle cost | Manual, specialist needed | High volume or haz | TRL 5, component proven | Large |
| 1 | Fails key limits | Highest lifecycle cost | Very complex, unreliable | Very high volume, hazardous | TRL < 4, lab concept | Very Large |

### Technology Scoring and Justification

The four technologies are scored based on the rubric, with justifications derived from the literature.

| Technology | Compliance Score | Cost Score | Complexity Score | Sludge Score | TRL Score | Footprint Score |
| --- | --- | --- | --- | --- | --- | --- |
| Microalgae Biosorption | 1 (Fails on B, unknown on others) | 2 (High biomass cost, uncertain CAPEX) | 1 (Biological process control is complex) | 3 (Moderate volume, likely hazardous) | 2 (TRL 3-5 for this application) | 2 (Large ponds or complex PBRs) |
| Chemical Precipitation | 3 (Meets most metal limits, fails B) | 3 (Low CAPEX, high sludge/reagent OPEX) | 4 (Robust, well-automated process) | 1 (Very high volume, hazardous sludge) | 5 (TRL 9) | 4 (Compact) |
| Ion Exchange (as Polisher) | 4 (Meets very strict limits, incl. B) | 2 (High OPEX due to regeneration/resin cost) | 3 (Automated but requires chemical handling) | 4 (Low solid waste, liquid regenerant) | 5 (TRL 9) | 5 (Very compact) |
| Activated Carbon (as Polisher) | 2 (Good for organics, poor for most ions) | 3 (Moderate CAPEX/OPEX) | 5 (Very simple passive system) | 4 (Low solid waste, requires regeneration) | 5 (TRL 9) | 4 (Compact) |

### Decision Matrix Table (Baseline Weights)

| Technology | Compliance (x0.30) | Cost (x0.25) | Complexity (x0.15) | Sludge (x0.15) | TRL (x0.10) | Footprint (x0.05) | Total Score | Rank |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Microalgae Biosorption | 0.30 | 0.50 | 0.15 | 0.45 | 0.20 | 0.10 | 1.70 | 4 |
| Chemical Precipitation | 0.90 | 0.75 | 0.60 | 0.15 | 0.50 | 0.20 | 3.10 | 1 |
| Ion Exchange (Polisher) | 1.20 | 0.50 | 0.45 | 0.60 | 0.50 | 0.25 | 3.50 | N/A* |
| Activated Carbon (Polisher) | 0.60 | 0.75 | 0.75 | 0.60 | 0.50 | 0.20 | 3.40 | N/A* |

*Ion Exchange and Activated Carbon are polishing steps and not directly comparable as standalone primary treatments. However, their high scores indicate their value as part of a hybrid system.

### Jurisdiction-Specific Sensitivity

The criteria weights are adjusted to reflect different regional priorities.

|  | EU (Strict) | US (Moderate) | China (Cost) |
| --- | --- | --- | --- |
| Compliance | 0.40 | 0.30 | 0.20 |
| Cost | 0.15 | 0.25 | 0.40 |
| Complexity | 0.15 | 0.15 | 0.15 |
| Sludge | 0.20 | 0.15 | 0.10 |
| TRL | 0.05 | 0.10 | 0.10 |
| Footprint | 0.05 | 0.05 | 0.05 |
| Winning Technology (Primary) | Chemical Precipitation (Score: 3.10) | Chemical Precipitation (Score: 3.10) | Chemical Precipitation (Score: 3.25) |

### Final Recommendation

Across all tested weighting scenarios, Chemical Precipitation remains the highest-ranked primary treatment technology. Its maturity, reliability, and effectiveness at removing the bulk of regulated metals outweigh its significant drawbacks in sludge production and inability to remove boron.

The analysis strongly suggests that a hybrid approach is necessary for full compliance, especially in jurisdictions with strict boron limits like the EU. The optimal configuration would be:

- Primary Treatment: Chemical precipitation to remove the bulk of Fe, REEs, and other precipitable metals.

- Secondary/Polishing Treatment: An Ion Exchange system using boron-selective resins to meet the stringent boron limits and remove any residual trace metals.

Microalgae biosorption, in its current state (TRL 3-5), is not a viable standalone solution for achieving regulatory compliance for complex NdFeB leachates. Its low scores in compliance, complexity, and TRL make it a high-risk option. However, if the challenges of iron interference and co-contaminant toxicity can be overcome through the proposed research, it could potentially serve as a lower-cost, greener polishing step to replace or augment ion exchange in the future, particularly if metal recovery from the biomass becomes economically viable.