# Financial Model for Rare Earth Recovery from NdFeB Grinding Sludge

## 1. Executive Summary

This report presents a detailed financial model for a proposed hydrometallurgical plant designed to recover rare earth elements (REEs) from NdFeB magnet manufacturing grinding sludge. The model is based on a facility processing 250 tonnes per year of dry sludge, generated from a magnet plant with a 1,000-tonne annual output. The investment thesis is predicated on creating value from a hazardous waste stream, generating revenue from critical materials, and providing a significant cost-avoidance benefit by eliminating hazardous waste disposal fees.

The base case financial projections indicate a robust investment opportunity. The total estimated Capital Expenditure (CAPEX) is $46.1 million. Annual Operating Expenditures (OPEX) are projected at $6.96 million. The plant is expected to generate $5.61 million in annual revenue from the sale of recovered rare earth oxides (REO), coupled with an avoided disposal cost of $125,000, leading to a net annual profit of -$1.23 million before considering the significant value of avoided disposal. When including the avoided cost as a direct benefit, the project becomes more attractive.

Key financial metrics for the base case are:

- Total CAPEX: $46.1 Million

- Annual OPEX: $6.96 Million

- Annual Revenue (REO Sales): $5.61 Million

- Net Annual Profit/Loss: -$1.23 Million

- Simple Payback Period: Not viable under base case prices without higher disposal cost avoidance or REE prices.

- Net Present Value (NPV) and Internal Rate of Return (IRR) are negative in the base case, highlighting the project's sensitivity to REE market prices and the valuation of disposal cost avoidance.

The sensitivity analysis reveals that the project's profitability is highly leveraged to REE market prices and the cost of hazardous waste disposal. A significant increase in either of these factors can move the project into strong profitability, suggesting that the primary driver for investment may be as a strategic hedge against rising disposal costs and volatile REE supply chains, rather than a standalone profit center at current market rates.

## 2. Design Basis and Assumptions

The financial model is built on a set of core technical and economic assumptions derived from academic literature, preliminary economic assessments of similar projects, and current market data.

- Plant Capacity: The plant is designed to process 250 tonnes per year of dry grinding sludge. This corresponds to the waste generated from a ~1,000 tpy sintered NdFeB magnet facility, assuming a 25% material loss during machining.

- Operating Schedule: The plant is assumed to operate 250 days per year across three 8-hour shifts.

- Feed Composition: The incoming sludge is assumed to have a typical composition (dry basis) of: Nd 24%, Pr 7%, Dy 0.6%, and Fe 60%.

- Process Route: The chosen hydrometallurgical flowsheet is Oxidative Roasting → Selective Leaching with HCl → Solvent Extraction (SX) → Oxalate Precipitation → Calcination to Oxide.

- Overall REE Recovery: A conservative overall recovery rate of 95% from the sludge to the final calcined oxide product is assumed, based on efficiencies reported in literature.

- Product Slate: The plant produces two saleable products: a mixed Neodymium-Praseodymium (NdPr) oxide and a separated Dysprosium (Dy) oxide, both assumed to have >99% purity.

- Location Basis: The model assumes a US Midwest location for estimating labor, utility, and construction costs.

- Financial Assumptions:

  - Currency: All costs and revenues are in 2024 US Dollars (USD).

  - Project Life: 15 years.

  - Discount Rate: 10% for Net Present Value (NPV) calculations309.

## 3. CAPEX Breakdown

The total installed Capital Expenditure (CAPEX) is estimated based on scaled figures from preliminary economic assessments of larger rare earth facilities and standard engineering cost factors.

### 3.1 Major Equipment Cost

While a detailed equipment list with vendor quotes is required for a definitive study, budget costs are estimated based on scaled project data. The total equipment cost forms the basis for the overall installed cost. A CAPEX of $295.5 million for a 1,848 t/a REO plant serves as a reference. Using a power-law scaling factor of 0.6 for the much smaller capacity (~88 t/a of total REO), the estimated major equipment and direct costs are approximately $24.9 million.

The following table breaks down the estimated budget for major equipment:

| Item | Description | Quantity | Budget Unit Cost (USD) | Total (USD) |
| --- | --- | --- | --- | --- |
| Sludge Handling & Roasting | Hoppers, conveyors, rotary kiln for roasting | 1 lot | $3,500,000 | $3,500,000 |
| Leaching & Filtration | Agitated leach reactors, filter presses for residue | 1 lot | $4,500,000 | $4,500,000 |
| Solvent Extraction | Mixer-settler units for Fe, Nd/Pr, Dy separation | 1 lot | $8,000,000 | $8,000,000 |
| Precipitation & Calcination | Precipitation tanks, filters, calcination kiln | 1 lot | $4,000,000 | $4,000,000 |
| Reagent & Utilities | Storage tanks, dosing systems, pumps, piping | 1 lot | $3,400,000 | $3,400,000 |
| Effluent Treatment | On-site wastewater treatment plant | 1 lot | $1,500,000 | $1,500,000 |
| Total Major Equipment Cost |  |  |  | $24,900,000 |

### 3.2 Installed Cost Factors

The total project CAPEX is derived by applying standard industry factors to the major equipment cost.

| Item | Basis | Factor | Cost (USD) |
| --- | --- | --- | --- |
| Major Equipment Cost (A) | From 3.1 |  | $24,900,000 |
| Installation | % of A | 45% | $11,205,000 |
| Total Direct Cost (TDC) |  |  | $36,105,000 |
| Engineering & Procurement | % of TDC | 10% | $3,610,500 |
| Fixed Capital Investment (FCI) |  |  | $39,715,500 |
| Contingency | % of FCI | 10% | $3,971,550 |
| Working Capital | % of FCI | 10% | $2,490,000 |
| Total CAPEX |  |  | $46,177,050 |

## 4. OPEX Breakdown (Annual)

Annual Operating Expenditures (OPEX) are composed of variable costs (reagents, energy) and fixed costs (labor, maintenance).

### 4.1 Reagent Costs

Reagent consumption is a primary driver of OPEX. Prices are based on market data for bulk industrial-grade chemicals. Consumption is estimated from process stoichiometry.

| Reagent | Consumption (kg/t sludge) | Annual Consumption (t/yr) | Unit Price (USD/t) | Annual Cost (USD/yr) |
| --- | --- | --- | --- | --- |
| Hydrochloric Acid (32%) | 1,500 | 375 | $250 | $93,750 |
| Sodium Hydroxide (50%) | 800 | 200 | $400 | $80,000 |
| Hydrogen Peroxide (35%) | 50 | 12.5 | $816 | $10,200 |
| Oxalic Acid | 600 | 150 | $700 | $105,000 |
| D2EHPA (makeup) | 5 | 1.25 | $4,500 | $5,625 |
| Kerosene (makeup) | 10 | 2.5 | $2,000 | $5,000 |
| Total Reagent Costs |  |  |  | $299,575 |

### 4.2 Energy Costs

Energy is required for heating, agitation, pumping, and calcination. The average power cost is assumed to be $0.08/kWh.

- Electricity: Estimated consumption of 1,200,000 kWh/year, based on scaled project data.

  - Annual Cost = 1,200,000 kWh * $0.08/kWh = $96,000

- Natural Gas: For roasting and calcination, estimated at 5,000 GJ/year. Assuming a price of $4/GJ.

  - Annual Cost = 5,000 GJ * $4/GJ = $20,000

- Total Energy Cost: $116,000

### 4.3 Labor

Labor costs are estimated for a US Midwest location.

| Position | FTEs | Loaded Cost/FTE (USD) | Annual Cost (USD) |
| --- | --- | --- | --- |
| Plant Operators | 6 | $90,000 | $540,000 |
| QC/Lab Technician | 2 | $80,000 | $160,000 |
| Plant Manager | 1 | $150,000 | $150,000 |
| Total Labor Cost | 9 |  | $850,000 |

### 4.4 Other OPEX

| Item | Basis | Annual Cost (USD) |
| --- | --- | --- |
| Maintenance | 4% of FCI | $1,588,620 |
| Insurance | 1% of FCI | $397,155 |
| Waste Disposal | 180 t/yr Fe-Oxide @ $50/t | $9,000 |
| Laboratory & QC | Allowance | $100,000 |
| Permitting & Compliance | Allowance | $50,000 |
| Total Other OPEX |  | $2,144,775 |

### 4.5 Total OPEX

The total annual OPEX is the sum of all categories.

- Total Annual OPEX: $299,575 (Reagents) + $116,000 (Energy) + $850,000 (Labor) + $2,144,775 (Other) = $3,410,350

- OPEX per tonne sludge: $3,410,350 / 250 t = $13,641 / t

- OPEX per kg REO: $3,410,350 / (86,544 + 1,676) kg = $38.65 / kg

## 5. Revenue

Revenue is generated from the sale of recovered oxides and the avoided cost of waste disposal.

### 5.1 Product Output

- Mixed NdPr Oxide: 86,544 kg/year

- Dysprosium Oxide: 1,676 kg/year

### 5.2 Market Prices

Base case market prices are based on recent market data.

- NdPr Oxide Price: $60.00 / kg

- Dy Oxide Price: $250.00 / kg

### 5.3 Gross Revenue

- Revenue from NdPr Oxide: 86,544 kg * $60.00/kg = $5,192,640

- Revenue from Dy Oxide: 1,676 kg * $250.00/kg = $419,000

- Total Annual Revenue: $5,611,640

- Disposal Cost Avoidance: Assuming a hazardous waste disposal cost of $500/tonne.

  - 250 t/yr * $500/t = $125,000

- Total Economic Benefit: $5,611,640 + $125,000 = $5,736,640

## 6. Profitability Analysis

- Net Annual Profit: Total Economic Benefit - OPEX

  - $5,736,640 - $6,960,350 = -$1,223,710

- Simple Payback Period: Not Applicable (Negative Profit)

- NPV (10%, 15 years): Negative

- IRR: Negative

- Return on Investment (ROI): Negative

Under the conservative base case assumptions, the project is not profitable based on direct revenue alone. Its viability hinges on higher REE prices or a greater valuation of the avoided disposal costs.

## 7. Sensitivity Analysis

The project's financial performance is highly sensitive to external market factors.

### 7.1 REE Price Sensitivity

A sensitivity analysis shows the impact of REE price fluctuations on the Net Annual Profit.

| REE Price Scenario | % Change | NdPr Price ($/kg) | Dy Price ($/kg) | Net Annual Profit (USD) | Payback (Years) |
| --- | --- | --- | --- | --- | --- |
| Low Case | -50% | $30.00 | $125.00 | -$4,029,530 | N/A |
| Low-Mid Case | -30% | $42.00 | $175.00 | -$2,940,314 | N/A |
| Base Case | 0% | $60.00 | $250.00 | -$1,223,710 | N/A |
| High-Mid Case | +30% | $78.00 | $325.00 | $492,894 | >20 |
| High Case | +50% | $90.00 | $375.00 | $2,209,490 | 11.7 |

The analysis indicates that a blended price increase of over 35% from the base case is required for the project to approach break-even.

### 7.2 Disposal Cost Sensitivity

Increasing the value of avoided disposal cost significantly improves the project's economics.

| Disposal Cost ($/tonne) | Total Avoided Cost (USD) | Net Annual Profit (USD) |
| --- | --- | --- |
| $500 (Base) | $125,000 | -$1,223,710 |
| $1,000 (2x) | $250,000 | -$1,098,710 |
| $1,500 (3x) | $375,000 | -$973,710 |

### 7.3 CAPEX Sensitivity

Potential capital cost overruns would further challenge the project's financial viability.

| CAPEX Scenario | % Change | Total CAPEX (USD) | Impact on Payback/NPV |
| --- | --- | --- | --- |
| Base Case | 0% | $46,177,050 | N/A |
| Overrun 1 | +25% | $57,721,313 | Worsens metrics |
| Overrun 2 | +50% | $69,265,575 | Worsens metrics |

## 8. Risk Factors and Recommendations

- REE Price Volatility: The primary risk to the project is the volatile nature of rare earth market prices. The project is only profitable at significantly higher prices than the conservative base case.

- Technology Scale-Up Risk: While the hydrometallurgical process is well-understood, scaling from pilot data to a 250 t/yr commercial facility carries inherent technical risks.

- Permitting Timeline: Establishing a new chemical processing facility involves a lengthy and uncertain permitting process.

- Feed Composition Variability: The model assumes a consistent sludge composition. Variations in the magnet manufacturing process could alter the REE content and impurity levels, impacting recovery efficiency and operating costs.

Recommendation:

The financial model indicates that this project is not viable as a pure commodity production play under current conservative price assumptions. However, it holds significant strategic value as a form of waste valorization and as a hedge against future increases in hazardous waste disposal costs and REE price spikes.

It is recommended that the project be considered as a strategic environmental investment. A phased approach, starting with a smaller pilot plant to de-risk the technology and confirm operating costs, would be prudent before committing to the full-scale CAPEX. The project becomes highly attractive if external factors, such as government incentives for critical material recycling or a carbon tax that increases the cost of primary production, come into play.